## Sheet1
Team Lead | Day | BackEnd | FrontEnd | Bug Fixing And BackUp | Issues Faced
Saurav Tiwari
25/09/2020
Task |  | 1. Login | 1. Login
|  | 2. Register User | 2. Register User
|  | 3. Send Email | 3. Send Email
|  | 4. Update Email | 4. Update Email
Members |  | Saurav | Ajay and Sonali | Saurav and Yogesh | Meeting Setup, Resolved*
26/09/2020
Task |  | 1. CSVtoSQL Library | 1. Admin Component
|  | 2. Add Question Set WebAPI | 2. Add Service
|  | 3. Remove Question Set WebAPI | 3. Delete Service
|  | 4. SQL Queries | 4. User Interface
Members |  | Saurav | Ajay and Sonali | Saurav and Yogesh | Git Issues, Resolved*