## Sheet1
Project Name : Online Examination Portal
User Story | TO DO | In Progress | To verify | Done
1. Database design 2. UI flow 3. Git and Github project setup | 1. Figure out the required tables and relationships between them. (Saurav & Yogesh) 2. To understand the case study and create a basic UI flow. (Ajay & Sonali) 3. Project creation with frontend and backend folders with Angular and WebApi projects. (Saurav & Ajay) | - | Verified | Task Completed (25/09)
1. DataBase Implementation in MSSQL | 1. Creation of Database Structure with key contraints in MS-SQL server. (Saurav & Ajay) | - | Verified | Task Completed(25/09)
1. Creation of Login/Register Page Component Users and Admins. | 1. Add a constant theme for the web app with material design and constant headers and footers. (Sonali) 2. Addition of Login page component in Angular project with navigations for student user page and admin user page. (Ajay & Saurav). 3. WebApi for fetching data, verifying users and adding users in the database. (Saurav) 4. Searching and implementing best logic for "forgot password" option and captcha. (Ajay) |  | Verified | Task Completed(25/09)
1. Question Set Addition and Removal 2. UI | 1. WebApi for Question Set addition and removal, their respective Sql table, components for admin model (Saurav) 2. UI (Ajay & Sonali) 3. Bug Fixing and Maintain Backup (Yogesh) |  | Verified | Task Completed(27/09)
1. Admin Module 2. Student Module | 1. WebApi for report and its filters,test and its filter (Yogesh & Saurav) 2.Admin Dashboard, Report View, and graphical display of Score, Question Preparation, Save As PDF, and Timer (Saurav,Ajay & Sonali) 3. Bug Fixing and Maintain Backup (Saurav & Yogesh) |  | Verified | Task Completed(29/09)
1. Test Conduct 2. | 1. Level 1,2 and 3 test FrontEnd (Ajay, Saurav and Sonali) 2.Student Dashboard, Report View, and graphical display of Score, Take Exam (Saurav,Ajay & Sonali) 3. Bug Fixing, Necessary Backend and Maintain Backup (Yogesh) |  | Verified | Task Completed(01/10)
Team Lead | Saurav Tiwari
Team Members | Ajay Upadhyaya
Sonali Dudve
Yogesh Narwal