## Sheet1
Team Lead | Date | BackEnd | FrontEnd | Bug Fixing And BackUp | Issues Faced
Saurav Tiwari
25/09/2020
Task |  | 1. Login | 1. Login | BackUp Done and Uploaded
|  | 2. Register User | 2. Register User
|  | 3. Send Email | 3. Send Email
|  | 4. Update Email | 4. Update Email
Members |  | Saurav | Ajay and Sonali | Saurav and Yogesh | Meeting Setup, Resolved*
26-27/09/2020
Task |  | 1. CSVtoSQL Library | 1. Admin Component | BackUp Done and Uploaded
|  | 2. Add Question Set WebAPI | 2. Add Service
|  | 3. Remove Question Set WebAPI | 3. Delete Service
|  | 4. Database Modification | 4. User Interface
Members |  | Saurav | Ajay and Sonali | Saurav and Yogesh | Git Issues, Resolved*
28/09/2020
Task |  | 1. Report Controller | 1. Admin DashBoard and Report | 1. Upload Controller Bug
|  | 2. Search filter for report | 2. AuthGuards | BackUp Done and Uploaded
3. Questions Prepared
4. Graphs, Pie Chart
Members |  | Yogesh | Saurav,Ajay and Sonali | Saurav and Yogesh | None
29/09/2020
Task |  | 1. Question Fetched | 1. Basic Test implemented | 1. Report Controller Bug
|  | 2. Result Insertion | 2. Timer | 2. Made SQL Queries Dynamic
|  |  | 3. Single Report | BackUp Done and Uploaded
4.Save As PDF
Members |  | Yogesh | Saurav,Ajay and Sonali | Saurav and Yogesh | None